## Sheet1
MSc Project - COMP702
Project Start Date : 05/06/2022 (Week 1)
Project Start Date : 23/09/2022 (Week 16)
Task | Status | Start Date | End Date | Time Period (in Weeks)
|  |  |  | Week 1 & 2 | Week 3 & 4 | Week 5 | Week 6 | Week 7-12 | Week 13 | Week 14 &15 | Week 16
Background reading and literature review. | DONE | 2023-06-05 | 2023-06-18
Project specification and design | DONE | 2023-06-19 | 2023-07-02
Finalize the development spec and design | DONE | 2023-07-03 | 2023-07-09
Specification and Design report and presentation slides | MILESTONE | 2023-07-14 | 2023-07-14 | Milestone 1 - 14/07/2023
Implentation &Testing of project simulation design | PROGRESS | 2023-07-10 | 2023-07-16
Continues Implementation And Testing Carla Simulation | TO DO | 2023-07-17 | 2023-08-20
Finalize software implementation and testing. | TO DO | 2023-08-21 | 2023-08-27
Final presentation slides deadline | MILESTONE | 2023-09-02 | 2023-09-02 | Milestone 2 - 02/09/2023
Start with the dissertation write-up. | TO DO | 2023-08-28 | 2023-09-17
Finalize the write-up of the dissertation. | TO DO | 2023-09-18 | 2023-09-22
Dissertation deadline | MILESTONE | 2023-09-23 | 2023-09-23 | Milestone 3 - 23/09/2023